## Slide 1: The HathiTrust Shared Print Program: From Planning to Implementation 2016 - 2019
Lizanne Payne
Shared Print Program Officer
elpayne@hathitrust.org
June 24, 2016
Print Archives Network (PAN) meeting, ALA Annual

## Slide 2: Background of the HathiTrust Shared Print Program
2011: Constitutional Convention “Distributed Print Monographs Archive Initiative” approved
2014: HathiTrust Print Monographs Archive Planning Task Force begins work
2015: Task Force planning report issued (March) and approved by PSC and Board (June)
2016: Shared Print Program Officer hired
Notes: Task Force report issued in March, endorsed by the PSC in June
four key characteristics

## Slide 3: Goals of the HathiTrust Shared Print Program
  Commit to retain print holdings that mirror book titles in the HathiTrust digital collection
  Maintain a lendable print collection distributed among HathiTrust member collections
  Reflect support by and provide benefits to all HathiTrust members (not a subset)
  Build on existing shared print and resource-sharing arrangements, avoid disturbing members’ other affiliations
From the final report of the HathiTrust Print Monographs Archive Planning Task Force (March 2015)

## Slide 4: Proposed approach: Build up to full coverage with early voluntary commitments
All HathiTrust institutions (~140)
All HathiTrust book titles ~7,200,000
Retention titles ~3,600,000
Seek to match 50% of the HathiTrust digital collection in Phase 1
Retention libraries
(10 – 30)
Ask each participant to retain at least 25% of their matching holdings
Adapted from the final report of the HathiTrust Print Monographs Archive Planning Task Force (March 2015)

## Slide 5: Proposed HathiTrust Shared Print Implementation Timeline
 | July 2016 – June 2017 | July 2017 – June 2018 | July 2018 – June 2019
Phase 1: Startup and Quick Launch Identify first-round participants Confirm policies and MOU Design and implement quick-launch systems support Identify and disclose first-round retention commitments (self-nominated) |  |  | 
Phase 2: Infrastructure and Operations Design and implement enhanced/permanent systems infrastructure Prioritize next-round retentions by collection analysis Identify next-round participants and retentions Plan for new services |  |  | 
Adapted from the final report of the HathiTrust Print Monographs Archive Planning Task Force (March 2015)

## Slide 6
Phase 1 Steps: Startup and Quick Launch
Policies & Agreements
Retention Commitments
Data & Systems
Appoint Shared Print Advisory Committee
Recommend policies & MOU
Identify prospective participants
Define quick launch systems
Identify matching holdings
Confirm & disclose retentions
HathiTrust SP collection available
June – December 2016
January – June 2017
Implement initial registry & resource-sharing
Approved by PSC & Board

## Slide 7: HathiTrust Shared Print Advisory Committee
Clement Guthro
Director of Libraries
Colby College
Jacob Nadal
Executive Director
ReCAP
Ken Peterson
Director of Access Services & the Harvard Depository
Harvard University
Matthew Revitt
Maine Shared Collection Librarian
University of Maine
Matthew Sheehy
Interim University Librarian
Brandeis University
Emily Stambaugh
Shared Print Manager
California Digital Library
Karla Strieb
Associate Director for Collections, Technical Services, and Scholarly Communication
Ohio State University
Thomas Teper
Associate University Librarian for Collections
University of Illinois, Urbana-Champaign
Ben Walker
Assistant Dean, Digital Services and Shared Collections
University of Florida
Lizanne Payne
Shared Print Program Officer
HathiTrust

## Slide 8: Thank You!